#### **Pioneer-8 Cruise Timeline**

V3 – 22 calendar days, adjusted for Navy Ops

28 – 29 May: Mobilization, LOSOS and WHOI pier

30 May – 20 Jun: Leg-1 (5 d), 1 d mob, Leg-2 (8 d), 1 d mob, Leg-3 (7 d)

21 Jun: Demob, WHOI pier and LOSOS

Timeline

30 May Complete loading, depart WHOI (1500)

31 May Recover ISSM-00004 anchor and ARM, Recover PMUI-00007 anchor

01 Jun Recover OSPM-00005 anchor and line pack, Recover OSPM

02 Jun Recover PMCO-00006 anchor, Recover PMUO-00004 anchor

03 Jun Arrive WHOI (0630), offload

04 Jun In-port WHOI, staging and loading for Leg 2, LARS test, prep OSSM for deployment

05 Jun Complete loading, depart WHOI (1330), recover glider(s)

06 Jun Deploy OSSM, CTD cast, deploy deep gliders (FZ, SS), CTD cast

07 Jun Recover OSPM (anchor only?), deploy OSPM, CTD casts

08 Jun Recover PMUO, deploy PMUO, CTD casts

09 Jun Recover OSSM, assess CN profiling glider, Deploy CNSM

10 Jun Recover CNSM, CTD cast, start along-shelf AUV survey

11 Jun Deploy shelf glider (EB), Complete AUV survey

12 Jun Arrive WHOI (0600), offload CSMs and CPMs, start loading for Leg 3

13 Jun In-port WHOI, staging and loading for Leg 3, prep ISSM for deployment

14 Jun Complete loading, depart WHOI

15 Jun Deploy ISSM, CTD casts, recover ISSM

16 Jun Recover PMCO, deploy PMCO, CTD casts

17 Jun Recover PMCI, deploy PMCI, CTD casts

18 Jun Recover PMUI, deploy PMUI, CTD casts

19 Jun Along-shelf CTD survey and/or complete primary objectives

20 Jun Arrive WHOI (0730), offload