Preliminary Cruise plan (as of 2017.07.27) for  Nov/Dec 2017 RV Armstrong ADEON deployment:

Table 1.  Research activity time requirements for cruise planning purposes, based on the assumptions of 10 kt ship transit speed, 8 kt ship acoustic survey speed. Departure port: Woods Hole, MA.  Return port: Woods Hole, MA. Shallow sites include: Virginia Intercanyon, Hatteras, 30oN-S, Charleston Bump, and Wilmington. Deep sites include: Savannah-D and 29oN-D (formerly 30oN-D). The transit and activities at the northernmost site (Virginia Inter-canyon) are calculated separately as the travel to/from that site is much larger than any other transits.

Activity						# of sites	time/site	Time required

[hrs]		[hrs]

Transit from WH to Virginia Intercanyon Stn. ~ 330 n.mi 		35		35

Virginia-Intercanyon Station  (first station 2X factor for all tasks)

Station Sampling – CTD and Net Casts	1*2		4		8

Mooring Deployments and Turnaround	1*2		8		16

Fine-scale acoustic survey transect		1*2		7		14

Calibration of AZFPs				1		6		6

Transit Virginia to Hatteras site (130 n.mi. )						15

Southernmost 6 Stations

Transits: Hatteras – Wilmington (125 n mi)		Wilmington – Savannah Deep (105 n mi)

Sav Deep – Charleston Bump (55 n mi)		Charleston Bump – 30N – Shall (130 n mi)

30 N Shal – 29 N Deep (125 n mi)			29 N Deep – Wilmington ( 280 n mi)

Wilmington – Hatteras (125 n mi) 	total loop 945 miles	95		95

Station Sampling

Shallow site CTD and Net Casts	4		4		16

Deep site CTD and Net Casts		2		8		16

Mooring Deployments and Turnaround

Shallow site				4		8		32

Deep site				2		12		24

Fine-scale acoustic survey (18km x 18km)	6		8		48

TL Experiment				2		48		48

Transit Hatteras to Virginia site (130 n.mi. )						15

Turnaround (pickup, download, redeploy Virginia)1		12		12

Transit from Virginia to WH	~ 330 n.mi 				35		35

Time Lost to Weather/Sea-State		5 days		24		120

subtotal	 555 hrs

Cruise total	 555 hrs = 23.1 days